## Sheet1
Dalmore in WWI
1. Research activity in WWI
a) visit Inverness
b) visit Alness Heritage centre
c) internet
2) Record remains
3) Create display panels for museum
4) Create leaflet for distillery
5) Create HER/Canmore entries. Add entries to Home Front Legacy Project
6) School visits (?try to get Alness academy pupils to record?)
? Signboard
? Visit to Edinburgh to look for wartime Aerial Photos
How to celebrate? Guided walk?
? Involving other groups: ?
UHI film
1. research |  | 8 x 2.5 hour sessions
2200 |  | includes prep. 11 days * 200/day
122.4 |  | travel. Assumes 35 miles x 8 trips x .45p per mile
408 |  | venue hire & catering. £17/hr x 3 hours x 8 sessions
200 |  | photocopying
250 |  | purchase of Aerial photos
1b. Visit to Alness Heritage Centre
200 |  | staff time: 2 visits
25.2 |  | travel
1c. Visit to Muirtown
200 |  | staff time
16.2 |  | travel
2. Recording Visits
800 |  | staff time: 4 visits
25.2 |  | travel
3. Create Display panels |  |  | 3x2.5 | NB: assumes also doing the leaflet, otherwise 4 days
600 |  | staff time
61.2 |  | travel
204 |  | venue hire
50 |  | display materials
250 |  | portable display boards
4. Create Leaflet |  |  | 4x2.5 hr sessions
800 |  | staff time
61.2 |  | travel
204 |  | venue hire
900 |  | Designer
500 |  | Printing
5. Canmore / HER entries
600 |  | 3 days
6. School visits
350 |  | ARCH time - can delete if others do it
25.2 |  | ARCH travel
7. Signboard
600 |  | designer
1000 |  | plinth & printing
8. Trip to NCAP to look at aerial photos
300 |  | train travel
350 |  | overninght accommodation
200 |  | staff time
9. Involving other groups:
UHI film
450 | creative writing for script? Guess.
255 | venue hire creative writing
Celebrating the project
Project Costs
800 |  | GIS work
2000 |  | Project Co-ordinator - 10 days @200 per day
400 |  | overheads (excl those covered in venue hire)
100 |  | office supplies
25 |  | NCAP online searching registration
40 |  | Northern Barrage Books
Evaluation: depending on funders, may have to budget more time to do this, or outside support#
Contingency:
Inkind
450 |  | admin
800 |  | Overall project management: 4 days @ £200
Total costs
16822.6
15657.4 |  | if delete display
14807.4 |  | if delete edinburgh trip
14432.2 |  | if delete school visits
Funding sources:
Costs formatted for funder X
[5 empty] | Actual Spend | Over/under | Invoice nos.
Project leader | 7950
Project travel | 336.6 | excludes Edinburgh trip
Venue Hire | 816
etc